## Requirements
ID | Section | Requirement | Description | Priority | Design brief page | In prototype | Status
R01 | Home | Club logo and name | Prominently displayed | Must have | Home | Home page | In prototype
R02 | Home | Mission statement or slogan | A brief tagline or mission statement | Must have | Home |  | Briefed
R03 | Home | Latest news | Headlines of the most recent club news or match results | Must have | Home |  | Briefed
R04 | Home | Upcoming fixtures | A short list of upcoming matches | Must have | Home | Home page | In prototype
R05 | Home | Featured player or match | Highlight a player or a recent or next match | Must have | Home |  | Briefed
R06 | Home | Quick links | Navigation to key sections | Must have | Home | Navigation | In prototype
R07 | About us | Club history | Background and history, founding date and key milestones | Must have | About us |  | Briefed
R08 | About us | Mission and values | The core mission, vision and values of the club | Must have | Mission and values | Navigation | In prototype
R09 | About us | Club achievements | Trophies, titles and significant achievements | Must have | About us |  | Briefed
R10 | About us | Management and staff | Profiles of management, coaching staff and key personnel | Must have | About us |  | Briefed
R11 | About us | Stadium | Home ground information, location and capacity | Must have | About us |  | Briefed
R12 | Team | First team squad | Player profiles: name, position, number, photo, bio, stats | Must have | Team fixtures and results |  | Briefed
R13 | Team | Coaching staff | Head coach, assistants and support staff | Must have | Team fixtures and results |  | Briefed
R14 | Team | Youth team | Profiles or list of youth and academy players | Must have | Team fixtures and results |  | Briefed
R15 | Team | Legends and former players | Former players who made significant contributions | Must have | Team fixtures and results |  | Briefed
R16 | Fixtures and results | Match schedule | Upcoming fixtures with date, time and opponent | Must have | Team fixtures and results | Home page | In prototype
R17 | Fixtures and results | Results | Recent results with scores and short summaries | Must have | Team fixtures and results |  | Briefed
R18 | Fixtures and results | League table | Current standings in the league or competition | Must have | Team fixtures and results | Home page | In prototype
R19 | Fixtures and results | Match reports | Detailed reports of past matches | Must have | Team fixtures and results |  | Briefed
R20 | News | Club news | Regular updates and articles about the club | Must have | Latest news |  | Briefed
R21 | News | Press releases | Official statements and announcements | Must have | Latest news |  | Briefed
R22 | News | Interviews | Interviews with players, coaches or management | Must have | Latest news |  | Briefed
R23 | News | Photo gallery | Images from matches, training and events | Must have | Latest news |  | Briefed
R24 | News | Video highlights | Match highlights and behind the scenes content | Must have | Latest news |  | Briefed
R25 | Membership and tickets | Ticket information | How to buy tickets for upcoming matches, with pricing | Must have | Membership |  | Briefed
R26 | Membership and tickets | Season tickets | Season ticket information and benefits | Must have | Membership |  | Briefed
R27 | Membership and tickets | Membership | How to join as a member, with benefits | Must have | Membership | Navigation | In prototype
R28 | Membership and tickets | Merchandise | Links to the online store | Must have | Shop | Navigation | In prototype
R29 | Academy and youth | Academy overview | The youth academy and its objectives | Later phase |  |  | Backlog
R30 | Academy and youth | Youth teams | The different youth teams and player profiles | Later phase |  |  | Backlog
R31 | Academy and youth | Training programmes | Sessions, camps and how to join | Later phase |  |  | Backlog
R32 | Academy and youth | Success stories | Academy graduates who reached the first team | Later phase |  |  | Backlog
R33 | Community and outreach | Community programmes | The club's community involvement and charity work | Later phase |  |  | Backlog
R34 | Community and outreach | Events | Upcoming events hosted or supported by the club | Later phase |  |  | Backlog
R35 | Community and outreach | Volunteer opportunities | How fans can get involved | Later phase |  |  | Backlog
R36 | Community and outreach | Sponsors and partners | Acknowledgment of sponsors and business partners | Later phase |  |  | Backlog
R37 | Fan zone | Supporters' club | How to join the supporters' club, with benefits | Must have | Fan zone |  | Briefed
R38 | Fan zone | Fan forums | A place for fans to discuss matches and players | Must have | Fan zone |  | Briefed
R39 | Fan zone | Social media links | Links to the club's social media profiles | Must have | Fan zone | Home page | In prototype
R40 | Fan zone | Fan polls and surveys | Interactive polls to engage the fan base | Must have | Fan zone |  | Briefed
R41 | Contact us | Contact form | A form for enquiries and feedback | Must have | Contact us | Navigation | In prototype
R42 | Contact us | Club address and map | Location of the club offices or stadium | Must have | Contact us |  | Briefed
R43 | Contact us | Phone and email | Contact details for general, ticketing and media enquiries | Must have | Contact us |  | Briefed
R44 | Contact us | Press and media contact | Contact information for media enquiries | Must have | Contact us |  | Briefed
R45 | Sponsorship and partnerships | Sponsorship opportunities | How businesses can sponsor the club | Must have | Sponsorship and partnerships | Home page | In prototype
R46 | Sponsorship and partnerships | Current sponsors | A list and description of current sponsors | Must have | Sponsorship and partnerships |  | Briefed
R47 | Sponsorship and partnerships | Partnerships | Partnerships with other organisations or brands | Must have | Sponsorship and partnerships |  | Briefed
R48 | Shop | Official merchandise | Online store for kits and club branded items | Must have | Shop | Navigation | In prototype
R49 | Shop | Special offers | Promotions or discounts on merchandise | Must have | Shop |  | Briefed

## Scope
Section | Items | Priority | Design brief page | In prototype | Briefed | Backlog
Home | 6 | Must have | Home | 3 | 3 | 0
About us | 5 | Must have | About us | 1 | 4 | 0
Team | 4 | Must have | Team fixtures and results | 0 | 4 | 0
Fixtures and results | 4 | Must have | Team fixtures and results | 2 | 2 | 0
News | 5 | Must have | Latest news | 0 | 5 | 0
Membership and tickets | 4 | Must have | Membership | 2 | 2 | 0
Academy and youth | 4 | Later phase |  | 0 | 0 | 4
Community and outreach | 4 | Later phase |  | 0 | 0 | 4
Fan zone | 4 | Must have | Fan zone | 1 | 3 | 0
Contact us | 4 | Must have | Contact us | 1 | 3 | 0
Sponsorship and partnerships | 3 | Must have | Sponsorship and partnerships | 1 | 2 | 0
Shop | 2 | Must have | Shop | 1 | 1 | 0
Total | 49 | 10 must have sections |  | 12 | 29 | 8

## Plan
Project plan | [6 empty] | Week 1 |  |  |  |  | Week 2
ID | Task | Owner | Phase | Start | End | Status | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
T01 | Kickoff and discovery call request | Business Analyst | Discover | 1 | 1 | Done
T02 | Discovery call with football manager | Business Analyst, Football manager | Discover | 2 | 2 | Done
T03 | Agree brand palette | Football manager | Discover | 2 | 2 | Done
T04 | Write website structure document | Business Analyst | Define | 3 | 3 | Done
T05 | Collect club content: mission, vision, values, history | Business Analyst, Football manager | Define | 3 | 6 | Done
T06 | Prioritise scope into must have pages | Business Analyst | Define | 6 | 7 | Done
T07 | Issue design brief to designer | Business Analyst | Design | 7 | 7 | Done
T08 | Build clickable Figma prototype | UI/UX designer | Design | 7 | 9 | Done
T09 | Prototype review with football manager | Business Analyst, Football manager | Review | 9 | 9 | Done
T10 | Apply review changes from the football manager | UI/UX designer | Review | 9 | 10 | In progress
T11 | Send revised prototype for sign off | Business Analyst | Review | 10 | 10 | To do
| Tasks done | 9 of 11
| Days planned | 10

## Board
Backlog | To do | In progress | Done
Academy and youth section (later phase) | Add league and accreditation marks | Fix prototype link on mobile | Discovery call with football manager
Community and outreach section (later phase) | Link the club's media channel |  | Collect club content
| Send revised prototype for sign off |  | Write website structure document
Agree brand palette and colour priority
Prioritise scope into must have pages
Issue design brief to designer
Build clickable Figma prototype
Prototype review with football manager
Cards
2 | 3 | 1 | 8